| Summary Milestone Schedule – List key project milestones relative to project start. |  |
| --- | --- |
| Project Milestone | Target Date (mm/dd/yyyy) |
| - Project Start | 01/01/20xx |
| - Complete Solution Design | 01/21/20xx |
| - Acquire Hardware and Software | 01/26/20xx |
| - Complete Solution Simulation with New Hardware/Software | 03/01/20xx |
| - Complete Solution Simulation and Testing | 04/01/20xx |
| - Deploy Solution | 05/01/20xx |
| - Project Complete | 05/15/20xx |

| Summary Budget – List component project costs |  |
| --- | --- |
| Project Component | Component Cost |
| - Personnel Resources | $110,000 |
| - Hardware | $45,000 |
| - Software and Licensing | $75,000 |
| - IT Lab Preparation | $15,000 |
| Total | $245,000 |

Project Charter

Project Title: Arkansas Films and Actors Initiative

Project Start Date: September 2025

Projected Finish Date: December 2027

Project Manager: Shequila Sledge

Instructor/Course: (Insert course name here)

Executive Summary

Arkansas has always had creative people and beautiful locations, but the film industry has not fully recognized the state’s potential. Other southern states like Georgia and Louisiana have built strong reputations for attracting film projects, while Arkansas has often been overlooked. However, films such as Sling Blade (1996) and Mud (2012) prove that Arkansas can be a powerful place for filmmaking. The Arkansas Films and Actors Initiative is designed to highlight Arkansas talent, filmmakers, and film-friendly sites. This project will not only support local artists but also boost the economy and create new pride in Arkansas’ contributions to the arts.

Project Purpose / Justification

The purpose of this project is to celebrate and promote Arkansas films and actors while giving the state more visibility as a filming destination. Arkansas actors often have to leave home to build their careers, and many films shot here do not get recognized for their Arkansas roots. This project changes that by building a platform, hosting a festival, and encouraging more producers to see Arkansas as a valuable filming location. The justification is simple: every film project can bring jobs, attract tourism, and build state pride, while also giving actors and filmmakers from Arkansas a chance to shine.

Business Objectives

- Create an online platform that highlights Arkansas actors, filmmakers, and film locations.

- Host the first Arkansas Film and Talent Festival by September 2026.

- Build at least 10 partnerships with production companies by the end of 2026.

- Help raise Arkansas’ reputation in the national film industry by the end of 2027.

Project Description

This project focuses on three major areas:

1. Digital Platform – A website that showcases actors and filmmakers from Arkansas with profiles, photos, and achievements. Featured actors will include Billy Bob Thornton (Sling Blade), Mary Steenburgen (Melvin and Howard), Wes Bentley (American Beauty), Joey Lauren Adams (Chasing Amy), and Gil Gerard (Buck Rogers in the 25th Century).

2. Film Festival – An annual Arkansas Film and Talent Festival that screens local films, recognizes Arkansas-born actors, and creates networking opportunities for professionals.

3. Industry Partnerships – Working with production companies to increase filming in Arkansas, using the success of past movies such as The Firm (1993), Walk the Line (2005), and True Grit (2010) to show the state’s value as a film location.

Success Criteria

The project will be considered successful if:

- The online platform is launched and actively used.

- The Arkansas Film and Talent Festival is successfully hosted.

- At least 10 production partnerships are created.

- Evidence shows an increase in films shot in Arkansas and recognition of Arkansas actors.

Requirements

- The online platform must be easy to use and highlight both talent and locations.

- A marketing plan is needed to promote the platform and festival.

- Support and cooperation from local communities, arts organizations, and tourism groups.

Constraints

- Limited funding, so the project will be tracked mainly by time and effort.

- Competition with states that already have larger film industries.

- Community support may take time to build.

Assumptions

- Arkansas actors and filmmakers will want to participate.

- Production companies are willing to explore Arkansas as a location.

- Local organizations will back the project.

Preliminary Scope Statement

In Scope:

- Films produced or shot in Arkansas.

- Actors and filmmakers from Arkansas.

- Cultural and economic impact of Arkansas film contributions.

Out of Scope:

- Films and actors not connected to Arkansas.

- Other entertainment industries such as music or theater.

Risks

- Other states may attract productions away from Arkansas.

- Low awareness of Arkansas as a filming destination.

- Slow participation from local communities or organizations.

Project Deliverables

- Launch of an online Arkansas Film & Talent platform with at least 10 actor/filmmaker profiles.

- Arkansas Film and Talent Festival held in September 2026.

- Partnerships with at least 10 production companies.

- Final evaluation report that measures the impact on local talent and film activity.

Reference Table: Arkansas Films and Actors

Film | Actor(s) from Arkansas | Notes

Sling Blade (1996) | Billy Bob Thornton | Thornton wrote, directed, and starred in this Oscar-winning film.

Mud (2012) | Wes Bentley (career ties) | Filmed in Arkansas; boosted recognition of local filming sites.

Chasing Amy (1997) | Joey Lauren Adams | Arkansas native, praised for her lead role.

Melvin and Howard (1980) | Mary Steenburgen | Won an Academy Award for Best Supporting Actress.

Buck Rogers (1979–1981) | Gil Gerard | Sci-fi TV star from Little Rock.

The Firm (1993) | (Filmed in Arkansas) | Showcased regional riverfront locations.

Walk the Line (2005) | (Filmed partly in Arkansas) | Biopic tied to Johnny Cash’s Arkansas roots.

True Grit (2010) | (Filmed partly in Arkansas) | Highlighted regional landscapes and history.

Summary Milestone Schedule

- Project Start: September 2025

- Digital Platform Completed: February 2026

- Marketing Campaign Launched: March 2026

- First Film Festival: September 2026

- Midterm Review: December 2026

- Final Evaluation: December 2027

Summary Budget (Tracked by Time)

- Planning and coordination: 3 months

- Building the online platform: 4 months

- Marketing and promotion: 2 months

- Festival planning and execution: 3 months

- Evaluation and reporting: 2 months

Total: About 14 months of active work

Project Approval Requirements

The project will be approved once the online platform is live, the first festival is held, and there is clear evidence of new partnerships and increased recognition of Arkansas talent.

Project Manager

The project manager will be responsible for timelines, planning, communication, and building industry connections to ensure that goals are met.

Authorization

Approved by Project Sponsor: ____________________

Date: ____________________

Arkansas Films and Actors Initiative

Project Charter

Shequila Sledge
Course: (Insert course name here)
Instructor: (Insert instructor name here)
Date: September 08, 2025

Table of Contents

Executive Summary ............................................. 2

Project Purpose / Justification ............................... 3

Business Objectives ............................................ 3

Project Description ............................................. 4

Success Criteria ................................................. 5

Requirements ..................................................... 5

Constraints ...................................................... 6

Assumptions ...................................................... 6

Preliminary Scope Statement ..................................... 7

Risks ............................................................ 7

Project Deliverables ............................................ 8

Summary Milestone Schedule ..................................... 9

Summary Budget ................................................ 10

Project Approval Requirements .................................. 11

Project Manager ................................................ 11

Authorization .................................................. 12

References / Works Cited

Thornton, Billy Bob. *Sling Blade*. Miramax, 1996.

Nichols, Jeff, director. *Mud*. Lionsgate, 2012.

Smith, Kevin, director. *Chasing Amy*. Miramax, 1997.

Demme, Jonathan, director. *Melvin and Howard*. Universal Pictures, 1980.

Larson, Glen A., creator. *Buck Rogers in the 25th Century*. NBC, 1979–1981.

Pollack, Sydney, director. *The Firm*. Paramount Pictures, 1993.

Mangold, James, director. *Walk the Line*. 20th Century Fox, 2005.

Coen, Ethan and Joel, directors. *True Grit*. Paramount Pictures, 2010.

Biographical information on Mary Steenburgen, Billy Bob Thornton, Wes Bentley, Joey Lauren Adams, and Gil Gerard sourced from IMDb and official actor biographies.